## Feedback 1
Owner Features | Validation and Comments Of Owner
Dashboard & Navigation
- Fully dynamic dashboard — zero hardcoded/dummy data, all counts live from Supabase | Dynamic Dashboard is Acceptable. Not able to validate what hardcoded dummy data is and counts from the supabase. This needs to be validated.
- Context-aware bell icon: routes to early-termination, payment disputes, rent roll, or messages depending on what's pending | Bell Icon is there. 3 Notifications of maintenance requests has been seen. Routes to early termination not known. Payments Disputes is okay Rent Roll is okay No pending rental so I could not test messaging on pending.
- Alert cards appear inline in dashboard scroll for each actionable item (terminations, disputes, processing payments) | Terminations not seen. To be validated Disputes Icon is available. However there is no archtiecture behind the icon. Processing of payments is not seen however Invoices and Quotes are active. Payment system needs to be validated.
- All dashboard tiles navigate correctly to their screens | The Dashboard is good and encapsulates everything that I can think of in the app.
Properties & Applications
- Application list grouped by property with a "Compare" button (podium icon) when 2+ active applicants | Application for rental not seen on owners dashboard.
- Application Competition screen — ranked applicants with score bars, shortlist/backup/select winner | Competition screen not seen.
- Application detail — "Request Holding Deposit" button wired with inline deposit status section | Request Holding deposit screen not able to be seen.
Holding Deposits
- Holding Deposits screen — cross-property tracker, filter chips (pending/paid/refunded), refund/apply-to-lease actions, create deposit modal | Holding Deposit screen is active. Paid & Active is seen and okay. To be tested in order to validate. Awaiting Payment tab is seen and okay. To be tested to validate Applied to lease tab is seen and okay. To be tested to validate Refunded tab is seen and okay. To be tested to validate Cross Property Tracker is not seen. Please explain wha this is. Explain what "Create to deposit Modal" is
- Live count on dashboard tile | Please validate where will this be on the dashboard.
Lease & Renewals
- Lease Renewals dashboard — expiring leases list, 80/60/40 day CPA notice tracker | Lease Renewal Icon works and shows Active all and Expired. To validate expiring system and how this will be. Can some dummy system be created.
- "Execute Renewal" button activates when tenant has accepted the offer | Execute renewal was not validated as there is no active leases booked on the system.
- Rent roll screen with payment reminder (fires notification to tenant) | Rent Roll is good. Meets all expectations.
Payments & Arrears
- Payment Disputes screen — all tenant disputes across all properties, Mark Under Review / Accept / Reject | Icon is active but no architecture
- Arrears Management screen with "Proposed Payment Plans" section — owner can review and reject tenant payment arrangements | There is an arreers management screen that shows Owed, Interests and tenants Was not able to validate proposed payment plans, accept and reject.
- Early Termination screen — review requests, accept/reject with penalty calculation; accepting auto-triggers deposit refund | Early termination screen was not seen under payment and areers. Advise where would this be.
Deposits
- Deposit Management screen — all deposits, interest accrual history, refund initiation | Screen is active. Shows total held and Interest accrued. Validate some live examples to see how the rest of the architecture would be
- Add Deduction modal + "Finalise Refund" button with full deduction breakdown | Not able to see this.
- Deposit interest accrual running as a Supabase Edge Function | This is seen and acceptable.
Maintenance
- Send PO screen properly routed and wired | No able to see this. Please clarify where this is.
- Maintenance detail: "Chat with Tenant" routes to messages, "Invoice" routes to invoices screen | Not able to do this as there was no tenant assigned or lease agreement. I think there are some "conditions" that need to be in place for this to work.
Inspections
- Inspections list with filter chips (All / Scheduled / In Progress / Pending Sig / Completed) | This architecture of this is great.
- Inspection Detail screen — clean read-only view (replaced the broken editor screen) | Was not able to move further as the condition for this to proceed is a an active lease agreement.
- Export PDF report matching client template: cover page, Actions Required table, per-room Ref/Clean/Undamaged/Working table, 3-column photo | Was not able to move further as the condition for this to proceed is a an active lease agreement.
grid with timestamps, declaration & signatures | Was not able to move further as the condition for this to proceed is a an active lease agreement.
Financial Reports
- Monthly Statements screen — SA-format owner statements with PDF export | Okay. Good
- Tax Report screen — SA tax year (March–Feb) ITR12 summary, 3-year history, PDF export | Okay. Good
- Invoices screen — combined rent + vendor invoices (two-tab view) | Okay. Good
Other
- Compliance screen — FICA tenant KYC status + property compliance checklist | Okay. Good
- Insurance Claims dashboard + individual claim screen (create, submit, track progress, upload documents) | Okay. Good
- Notifications screen | Okay. Good
- Documents hub | Okay. Good
- Messaging fully wired (thread list + thread view + compose) | Not able to see this. The messaging can happen between multiple avenues. This can be valided when a complete lease is done to be tested.
- PDF statements saved to Documents so tenant can also access them | Need to validate. Could not been seen.
---
Tenant Features
Dashboard
- Fully dynamic: upcoming viewings, pending applications, activity feed (all tappable) | Okay good
- Activity feed items route to correct screens | Okay good. This needs to be validated.
- Progress tracker component showing lease journey stage | No able to see this as there has been no lease active.
Applications & Onboarding
- Application status screen — grouped Approved/Active/Past, holding deposit payment banner | Application screen exists. Give Navin Indraj to be owner and Nashin Indraj to be tenant.
- Post-submission routes to application status (not back to dashboard) | Exists. To be valided.
- Self-registration screen — create account directly from login (email, password, full name, role) | Okay good.
- Relaxed validation for testing: no 18+ age check, employer/income optional | Prof of income and Reference should be pdf upload and not photo
Lease & Renewals
- Lease Renewal screen — expiry countdown, CPA notice timeline, accept/counter/reject offers from owner | Exists. No active leases to be able to validate.
Payments & Arrears
- Arrears screen — escalation stage badge, CPA cure period countdown, legal rights banner, propose payment arrangement modal | Able to see this in owners screen. Not in tenant screen. Not able to see this as there is no active lease. Arreers not able to be seen. CPA countdown not able to be seen. Legal rights banner not able to be seen. Propose payment arrangement model is not able to be seen.
- Payment Disputes screen — raise and track disputes | Payment dispute could be seen on owner but not on tenant. Payment disputs on tenant screen not able to be seen.
- "Arrears & Escalations" quick-access button on the payments screen | Arreers and escalation seen on owners but not tenants. Arreers and escalation not able to be seen as thelease has probably not been loaded.
Holding Deposits
- Holding Deposit screen — active/history deposits, payment countdown, "I Have Paid" confirmation, RHA s5A rights displayed | Holding deposit is seen on owners but not on tenants screen.
Deposit
- Deposit Status screen — balance, interest accrual, deductions, RHA rights summary | Not able to see this on tenant screen.
Maintenance
- Maintenance list, report, and detail screens | Okay good
- Work verification screen — approve or reject completed work with photo evidence | Could not report an issue as there was no active lease.
- Reports screen — pending verifications + inspection history in one place | Could not validate this as there is no active lease.
Inspections
- Inspection history visible in Reports screen with type, status, condition, signature status | Inspections not seen on tenants screen. This is needed.
Documents
- Documents screen — ID docs, proof of income, inspection reports, lease PDFs all in one place | This is okay.
Messaging
- Full thread list + thread view | Messages icon exists. Need to validate.
- Compose new message — pre-fills owner from active lease, subject + category picker | Could not message as there is no active lease
Early Termination
- Early termination request screen with penalty calculation breakdown | Not able to see early termination icon.
---
Infrastructure & Legal Compliance
- 36 database migrations applied — arrears, disputes, renewals, holding deposits, deposit lifecycle, insurance claims, notifications, POPIA | Not shown in tenants profile but seen in owners
tables
- Legal interest on arrears (Prescribed Rate of Interest Act) replacing illegal flat late fees | Not shown in tenants profile but seen in owners
- CPA cure periods on arrears escalation | Not shown in tenants profile but seen in owners
- POPIA consent capture + DSAR request system | Not shown in tenants profile but seen in owners
- Viewing expiry automation (server-side via Supabase) | Not shown in tenants profile but seen in owners

## Feedback 2
Dashboard |  | Comments | Comments June 26
1 | Open dashboard — should see property count, active lease, rent roll stats, alert cards for overdue rent and open maintenance | Propert Count is seen. Active lease is seen Vacant lease is seen Rent roll stats is seen. Overdue rent is also seen Open maintenance is also seen. | OKAY
2 | Tap the bell icon — should see 5 notifications (maintenance, overdue rent, application, viewing request, unread message) | 5 Notifications seen and 1 application received | OKAY
Viewing Requests |  | Comments
3 | Go to Viewings — should see a pending viewing request for "106 Cerise Monavoni" on 12 April | Able to see this. Was not able to reject or accept as the viewing date has expired. | OKAY
4 | Approve or Decline the viewing — try approving with a confirmed time, OR decline with an alternate time suggestion | This seems to be a smart system as it expired as the date was 12th April. This should also appear on the bell icon. | OKAY
Rental Applications |  | Comments
5 | Go to Applications — should see a submitted application from Nashin Indraj for "4A Dolphin" (score 78, low risk) | This was accessed thorugh the bell icon. Is there not a separate button for this? | OKAY
6 | Review the application — check applicant details (employer, income, affordability ratio) | The architecture is good here. I need to understand how this works in getting 31%. | CLARIFCATON REQUIRED
7 | Accept or Reject the application — if accepted, proceed to offer a lease Lease Management | Architecture is good and simple. I followed the process to create a lease agreement. I think a standard format template needs to be added. I will share a lease agreement template. | Create Lease Agreement Write on PDF needs to be pulled up with all the details in it.
Lease Management |  | Comments
8 | Go to Leases — should see the active lease on "4B Dolphin Crescent" (Jan–Dec 2026, R12,000/mo) | Yes. This is now active. | There is a simple overview screen. Linked to the above point. PDF needs to be uploaded.
9 | View lease details — check deposit info (R15,000 at FNB, 7.25% interest), payment due day, escalation terms | Okay. But please walk me thorugh this. I may need some explanation here. | Calculation needs to be understood.
10 | Contact Tenant — tap "Contact Tenant" → should offer Message option that opens messaging | Messaging works. There is a visual issue here. When keyboard pops up, I cannot see what I am typing. | Messaging works. There is a visual issue here. When keyboard pops up, I cannot see what I am typing.
Payments / Rent Roll |  | Comments
11 | Go to Rent Roll — should see 4B Dolphin Crescent with April rent overdue (R12,000 pending) | Okay. Confirmed. | okay
12 | Send Payment Reminder — tap reminder button → notification should fire to tenant | Was able to do this. | okay
Maintenance |  | Comments
13 | Go to Maintenance — should see "Geyser leaking in main bathroom" (high priority, open) and "Garden gate latch broken" (medium, acknowledged) | Functionality works to push to dedicated vendors and open market. Was not able to see this work as dedicated vendors have not been loaded. I would like to set some dedicated vendors up. | For this to take place the vendors need to be allocated in the applcation.
14 | Open the geyser request — acknowledge it, then try assigning a vendor or routing it | Functionality works to push to dedicated vendors and open market. Was not able to see this work as dedicated vendors have not been loaded. I would like to set some dedicated vendors up. | For this to take place the vendors need to be allocated in the applcation.
15 | Chat with Tenant — should open messaging screen inspections | Messaging works. There is a visual issue here. When keyboard pops up, I cannot see what I am typing. | okay
16 | Go to Inspections — should see the scheduled periodic inspection for 15 April on 4B Dolphin Crescent | Okay | okay
17 | Open inspection → should show room-by-room checklist (10 rooms, condition ratings, photo capture) | This could not be seen . Could not open room by room to see the inpsection. | OKAY
18 | Try conducting: rate a few rooms, take/pick photos, add notes, save progress | No able to test this functionality as it does not exist. | OKAY
Messaging |  | Comments
19 | Go to Messages — should see thread "Geyser leak — urgent" with 3 messages, 1 unread from tenant | This works fine | OKAY
20 | Reply to the tenant's message | This works fine | OKAY
Properties |  | Comments
21 | Open any property — check photos load (4B Dolphin Crescent has images) | Added more photos. When I go to the edit screen I can see the added photos. The photoes are not uploading/refreshing to the viewing screen. | OKAY
22 | Add a new property — pick photos, fill details, save — verify images upload and appear | Was able to create 12E Ocean Drive | OKAY
23 | Edit an existing property — add a photo, save — verify new photo appears | Was able to do this. | OKAY
TENANT Test Tasks (login as navin.indraj@yahoo.com)
Dashboard |  | Comments
24 | Open dashboard — should see active lease card (4B Dolphin Crescent, R12,000/mo), upcoming inspection alert, overdue rent warning | Was able to see the lease card. However the downloadable lease was not able to be seen. | Was able to see the lease card. However the downloadable lease was not able to be seen.
25 | Tap the bell icon — should see 4 notifications (inspection scheduled, rent overdue, viewing confirmed) | Was able to see this. | OKAY
26 | Check "Complete Your Profile" section — if proof of address is not uploaded, it should show as missing; if uploaded, should show orange clock "pending verification" | Only able to upload photos. Was not able to access my documents from my phone.
Profile |  | Comments
27 | Go to Profile — fill in any missing fields (ID number, phone, date of birth) | okay | OKAY
28 | Upload Proof of Address — pick an image → should show "Uploaded — pending verification after success | Only able to upload photos. Was not able to access my documents from my phone. | OKAY
29 | Return to Dashboard — proof of address should now show orange "pending" status | yes. This is showing pending verification | OKAY
Lease |  | Comments
30 | Go to Lease — should see active lease details, deposit info (R15,000 + R362.50 interest accrued) | I am logged on as the tenant. The property name is not on my lease page. Lease Period: 01/01/2026 to 31/12/2026 Monthly Rent R12000 This is good and okay Deposit Paid R15000 Payment Date 1s of every month | OKAY
31 | Contact Owner — tap → should offer Message option | I was able to to conduct messaging smoothly. | OKAY
Payments |  | Comments
32 | Go to Payments — should see Jan/Feb/Mar completed, April overdue (R12000) | Yes I was able to see this on Recent Payments | OKAY
33 | Tap "Make Payment" on April rent — test the payment flow (mock) | Yes the payment functionality works. Now the next step is to link the payment portal | OKAY
34 | Check Arrears section — should show April is overdue with interest accruing | This was no more arreers as payment was done | OKAY
Maintenance |  | Comments
35 | Go to Reports — should see maintenance history | Was able to see maintenance history | OKAY
36 | Submit a new maintenance request — describe an issue, attach a photo | On the property icon the description of the property should be there. I was able to log the maintenance request. I was able to upload a photo already taken. Not able to use camera live to take a photo. I took the photo but was not able to upload. | OKAY
37 | Check existing requests — should see geyser and garden gate issues | Geyser and Gate isssue have been listed. My new request above has also been uploaded. | OKAY
Messaging |  | Comments
38 | Go to Messages — should see "Geyser leak — urgent" thread | Issue details are good. Its open and High Priority Description is nicely laid out with date and time stamps Progress milestones are on the button. | OKAY
39 | Read messages — 3 messages in thread | Messages threads are there and good. But I cannot access messages from Maintenance list screen. To do this I must go back to the messages screen. | OKAY
40 | Send a new message to owner — compose a new thread or reply | Done. This works instantaneoulsy.
Inspection |  | Comments
41 | Check dashboard — should show "Upcoming Inspection" alert for 15 April | App crashes when this is activated | OKAY
42 | Tap inspection alert — should open inspection detail | App crashes when this is activated | OKAY
Viewing & Application Status |  | Comments
43 | Check viewing history — should see completed viewing at 4A Dolphin | This was not seen on the tenant side | OKAY
44 | Check application status — should see submitted application for 4A Dolphin | This was not seen on the tenant side | OKAY